## ADC Requirements Matrix
Req. ID | Status | ADC SUBSYSTEM REQUIREMENTS | How Requirement Will Be Met | Rationale | Color Code
ADC-01 | In progress | The ADC Subsystem, on hard start, shall provide a Single Frame attitude solution within 5 minutes of gaining position knowledge | Attitude determination algorithm using IMU sensor fusion, magnetometer, gyro propagation, and onboard position knowledge | Logistics TBD, but the spacecraft must be able to deduce its attitude from its position and sensor measurements alone | B- dot Detumbling Controller
ADC-02 | In progress | The ADC Subsystem shall solve for attitude in both sunlight and eclipse | Magnetometer + gyro based attitude determination independent of sunlight conditions | ARES needs attitude knowledge whenever it makes observations, and it will be making observations in sunlight and eclipse | Attitude Determination / Sensor Fusion Algorithm
ADC-03 | In progress | The ADC Subsystem shall report spacecraft pitch to an accuracy of ±10 deg with respect to the spacecraft Reference Frame | Sensor fusion and attitude estimation filtering | Accurate attitude knowledge is important information for the reaction side of ARES | Uncertainty Estimation Algorithm
ADC-04 | In progress | The ADC Subsystem shall report an estimate of spacecraft pitch uncertainty | Covariance/error estimation from attitude filter | ARES will use whatever attitude accuracy it can get, but it also needs to know what accuracy its working with in order to compensate | Magnetic Alignment Controller
ADC-05 | In progress | The ADC Subsystem shall report spacecraft yaw to an accuracy of ±10 deg with respect to the spacecraft Reference Frame | Sensor fusion and attitude estimation filtering | Accurate attitude knowledge is important information for the reaction side of ARES | Position / Navigation Algorithm
ADC-06 | In progress | The ADC Subsystem shall report an estimate of spacecraft yaw uncertainty | Covariance/error estimation from attitude filter | ARES will use whatever attitude accuracy it can get, but it also needs to know what accuracy its working with in order to compensate | SOH / Telemetry Monitoring
ADC-07 | In progress | The ADC Subsystem shall report spacecraft roll to an accuracy of ±10 deg with respect to the spacecraft Reference Frame | Sensor fusion and attitude estimation filtering | Accurate attitude knowledge is important information for the reaction side of ARES
ADC-08 | In progress | The ADC Subsystem shall report an estimate of spacecraft roll uncertainty | Covariance/error estimation from attitude filter | ARES will use whatever attitude accuracy it can get, but it also needs to know what accuracy its working with in order to compensate
ADC-09 | Mostly Complete | The ADC Subsystem shall control rotation rate to be no more than 5 deg/sec/axis | B-dot controller. Magnetometer readings will ->B-dot law. Gyroscope readings after mtq commands have been sent -> req. verification. ADC 09:desired operational detumbled target | Rotation rates need to be low for communication and picture taking
ADC-10 | In progress | The ADC Subsystem shall align the Z-axis of the spacecraft with the local Earth magnetic field vector to within an accuracy of ±10 deg/axis | Magnetic field pointing controller using MTQs after detumbling. Hystheresis rods guarantee passive magnetic stabilization (no software commands) and passive magnetic alignment. | Magnetic field aligning the z-axis will allow the payload sensors to rotate from zenith to nadir and back
ADC-11 | Not Started | The ADC Subsystem shall report position to an accuracy of 100m | GPS receiver and onboard navigation estimation. GNSS | Accurate position knowledge is important information for the reaction side of ARES
ADC-12 | Not Started | The ADC Subsystem shall report an estimate of position uncertainty | GPS covariance/error reporting. GNSS | ARES will use whatever position accuracy it can get, but it also needs to know what accuracy its working with in order to compensate
ADC-13 | In progress | The ADC Subsystem shall determine the orientation of a face onboard the spacecraft at 1/5 Hz | Attitude quaternion estimation and body-frame orientation calculations | The spacecraft will be calculating its attitude, but all ARES cares about is where the cameras are pointing
ADC-14 | Mostly Complete | The spacecraft shall not exceed a rotational rate of ±20 deg/s/axis after the damping period is completed | B-dot detumbling controller with MTQ saturation limits guaranteeing safety and stability. | A stable rotational rate is important both for establishing communications links with the radios and for the payload
ADC-15 | Not Started | The ADC subsystem shall report the operational state of every ADC sensor to the CDH subsystem as SOH data at a rate of 1 report per minute | Health monitoring telemetry and sensor status reporting to CDH | SOH data to be aggregated by the CDH subsystem
ADC-01 | Once GNSS position and time become valid, the TRIAD algorithm computes a single-frame attitude solution using measured Sun and magnetic field vectors and reference Sun and magnetic field vectors. The computation executes in significantly less than 5 minutes, satisfying ADC-01.
ADC-02 | Need to figure out how solve for attitude during eclipse because without light, photodiodes = 0 and we don’t have a valid sun body. Probably what will be done is get the last valid TRIAD attitude + gyro rates and propagate attitude through eclipse.
ADC-03 | Measured Sun and magnetic field vectors are combined with SPICE/IGRF reference vectors in the TRIAD attitude determination algorithm. The resulting attitude matrix is converted to Euler angles, providing spacecraft pitch.
ADC-04 | Using a list of 100 readings the uncertainty at a confidence of 95% can be calculated using student t distribution
ADC-05 | Measured Sun and magnetic field vectors are combined with SPICE/IGRF reference vectors in the TRIAD attitude determination algorithm. The resulting attitude matrix is converted to Euler angles, providing spacecraft yaw.
ADC-06 | Using a list of 100 readings the uncertainty at a confidence of 95% can be calculated using student t distribution
ADC-07 | Measured Sun and magnetic field vectors are combined with SPICE/IGRF reference vectors in the TRIAD attitude determination algorithm. The resulting attitude matrix is converted to Euler angles, providing spacecraft roll.
ADC-08 | Using a list of 100 readings the uncertainty at a confidence of 95% can be calculated using student t distribution
ADC-09 | Once the IMU gives us the the magnetic field readings in the 3 axis, bdot can be computed and, with bdot control law, we know the dipole moment needed to be commanded to each mtq. The current code tracks the angular velocity in each axis and reports STABLE or SPINNING state. Right now we only have one PWM and DIR pin, the future bdot code should include the other 2 h-bridge channels.
ADC-10
ADC-11
ADC-12
ADC-13
ADC-14 | Once the IMU gives us the the magnetic field readings in the 3 axis, bdot can be computed and, with bdot control law, we know the dipole moment needed to be commanded to each mtq. The current code tracks the angular velocity in each axis and reports STABLE or SPINNING state. Right now we only have one PWM and DIR pin, the future bdot code should include the other 2 h-bridge channels.
ADC-15